## QA
|  | MISSISSIPPI DEPARTMENT OF TRANSPORTATION | [5 empty] | Page 1 of 2
|  | QUANTITY ADJUSTMENT | [6 empty] | Information is for example only and should be removed when starting a new quantity adjustment.
1. | QUANTITY ADJUSTMENT NO. 1 |  |  |  | 2. DATE: 5/3/2013
3. | PROJECT NO. IM-0020-01(165) / 103914303000 |  |  |  | 4. LPA: CITY OF HORN LAKE
5. | COUNTY: Hinds
6. | The following changes on the above project with stations, quantities, and items involved are recommended
for the reasons stated in detail:
Pay Item | Description | Previous | Revised |  | Increase | Unit | Unit | Amount
|  | Quantity | Quantity |  | or |  | Price
Decrease
234-A001 | Temporary Silt Fence | 5000 | 150 |  | -4850 | LF | 5 | -24250
406-A001 | Cold Milling of Bit Pav, All Depths | 444120 | 380600 |  | -63520 | SY | 1.3 | -82576
907-249-A001 | Riprap for Erosion Control | 650 | 0 |  | -650 | TON | 74 | -48100
907-249-B001 | Remove and Reset Riprap | 100 | 0 |  | -100 | CY | 130 | -13000
907-304-A001 | Granular Material, LVM, Class 5, Gr C | 1000 | 30000 | - | 29000 | CY | 27 | 783000
907-403-AA002 | SMA, 12.5 mm Mixture | 37200 | 33939.12 |  | -3260.88 | TON | 102.15 | -333098.892
907-403-M003 | WMA, ST, 12.5 mm Mixture | 20000 | 11296.15 |  | -8703.85 | TON | 64.47 | -561137.2095
907-403-M010 | WMA, HT, 12.5 mm Mixture | 9000 | 7454 |  | -1546 | TON | 60.66 | -93780.36
907-403-N008 | WMA, HT, 9.5 mm Mixture | 6000 | 600 |  | -5400 | TON | 73.22 | -395388
[7 empty] | TOTAL | -768330.4615
REASONS:
234-A001 Temporary Silt Fence, 907-249-A001 Riprap for Erosion Control, and 907-249-B001 Remove and Reset Riprap - The original quantities for the project included 16 acres of clearing and grubbing in according with the MDOT Clearing Policy. Later, it was seen that the MDOT did not have the money to do the clearing but the erosion control items were not reduced when the clearing was eliminated.
406-A001 Cold Milling of Bituminous Paving, All Depths - All of the superelevations on the curves were checked and adjusted during the milling process. The corrections to the superelevations of the curves caused much of the milling in the curves to daylight out in the middle of a lane causing a portion of one lane and all of one shoulder not to require milling in several curves.
907-304-A001 Granular Material, LVM, Class 5 Group C - During the submittal process for the project, District 3 inadvertently left a zero off the quantity, therefore making the corrected quantity 10,000 cubic yards. Furthermore, the gravel quantity was figured on a 1.5 inch depth which is the net difference in the overall pavement thickness. Upon beginning shoulder work, areas where the super-elevation rates on the curves were corrected created significantly deeper edge of pavement to existing gravel differentials. Also, in many areas the safety slope does not exist and therefore must be reconstructed with granular material causing this item to over run.

## Worksheet
|  | WORKSHEET |  |  |  | Page 2 of 2
QUANTITY ADJUSTMENT NO. 1 |  |  | PROJECT NO. IM-0020-01(165) / 103914303000 |  |  |  | Enter only areas in red
7. Total Cost per Gov. Est. dated |  | Est. Date |  |  |  | 0 | a+b+c
|  |  | Participating | Non-Participating
a. Contingencies |  |  | 0 | 0 |  |  | from gov est
b. Construction |  |  | 0 | 0 | 0 |  | from gov est
c. CE&I |  |  | 0 | 0 |  |  | from gov est
8. Previous Quantity Adjustments to this Gov. Est. |  |  | 0 | 0 | 0 |  | from previous QA's
9. This Quantity Adjustment |  |  | 0 | 0 | 0 |  | from page 1
10. CE&I Adjustments dated |  | SA Date if $ added | 0 | 0 |  |  | from CE&I SA's
11. Rev. Total Est. Cost of Project |  |  | 0 | 0 | * | 0
* Note: If line 11 is greater than line 7, then a revised government estimate is required.
12. | Federal match % | 80% |  |  |  |  | from gov est
|  | federal portion if not above the maximum awarded |  |  | 0
13. Original Federal Funds Requested |  |  |  | 0 |  |  | from gov est
14. Current Estimated Federal Portion |  |  |  | 0 |  |  | =(participating from line 11)*(Federal Match % from line 12); not to exceed federal limit
15. Original Estimated Local Portion |  |  |  | 0 |  |  | 7-13
16. Current Estimated Local Portion |  |  |  | 0 |  |  | 11-14
Recommended for Approval
|  | LPA Project Engineer / Architect |  |  | Date
Approved
|  | LPA Official |  |  | Date