## Table 1
LIQUIDATED DAMAGES FOR PROJECTS WITH WORKING DAYS
Project No.: | County: |  | Fill in cells highlighted in green
LOCAL PUBLIC AGENCY:
Original Notice to Proceed Date:
(a) Original working days for the project:
(b) Working days by supplemental agreement:
(c) Working days by increase in quantities: |  |  | Do not include inc. quan. that already has time given by S/A
(d) Final working days: (Sum a+b+c) | 0
(1) Date all working days used: |  |  | Use date final working days were assessed from CSD-765
(2) Date Contractor requested final inspection
(3) Date Final Inspection was made
(4) Date Contractor received punch list in writing
(5) Date punch list items completed
A GROSS LIQUIDATED DAMAGES--------------------------------------------------------- |  | 0
(Calendar days between (1) and (5))
ADJUSTMENT FOR NO TIME CHARGED DAYS
(6) Days with no work awaiting asphalt curing for stripe |  |  | All pay items except stripe must be complete for this adjustment to apply
(7) Days between request for final inspection -------------------------------
and written punch list (Days between (2) and (4))
(8) Days between the date that the contractor received punch list in ---
writing and completion of all punch list items. (Maximum 7 if in
Liquidated Damages and 14 if not in Liquidated Damages)
B TOTAL ADJUSTMENTS (Sum 6+7+8) ----------------------------------- |  | 0
C TOTAL DAYS ON LIQUIDATED DAMAGES (A-B) ------------------- |  | 0
(If A-B <0 then C = 0)
D Total Original Construction Cost
E Liquidated damages per day |  |  | From 907-108.07
TOTAL LIQUIDATED DAMAGES (C*E): |  | 0
(C X E)
_________________________________
Project Engineer / Architect
LIQUIDATED DAMAGES FOR PROJECTS WITH CALENDAR DAYS
Project No.: | County: |  | Fill in cells highlighted in green
LOCAL PUBLIC AGENCY:
Original Notice to Proceed Date:
(a) Original calendar days for the project:
(b) Calendar days by supplemental agreement:
(c) Calendar days by increase in quantities: |  |  | Do not include inc. quan. that already has time given by S/A
(d) Final calendar days: (Sum a+b+c) | 0
(1) Date all calendar days used: | 0
(2) Date Contractor requested final inspection
(3) Date Final Inspection was made
(4) Date Contractor received punch list in writing
(5) Date punch list items completed
A GROSS LIQUIDATED DAMAGES--------------------------------------------------------- |  | 0
(Calendar days between (1) and (5))
ADJUSTMENT FOR NO TIME CHARGED DAYS
(6) Days with no work awaiting asphalt curing for stripe |  |  | All pay items except stripe must be complete for this adjustment to apply
(7) Days between request for final inspection -------------------------------
and written punch list (Days between (2) and (4))
(8) Days between the date that the contractor received punch list in ---
writing and completion of all punch list items. (Maximum 7 if in
Liquidated Damages and 14 if not in Liquidated Damages)
B TOTAL ADJUSTMENTS (Sum 6+7+8) ----------------------------------- |  | 0
C TOTAL DAYS ON LIQUIDATED DAMAGES (A-B) ------------------- |  | 0
(If A-B <0 then C = 0)
D Total Original Construction Cost
E Liquidated damages per day |  |  | From 907-108.07
TOTAL LIQUIDATED DAMAGES (C*E): |  | 0
(C X E)
_________________________________
Project Engineer / Architect