## Sheet1
| Form CSD-612LPA | [5 empty] | PROGRESS SCHEDULE | [41 empty] | PROJECT NUMBER
Rev. 1/2021
COUNTY
|  |  | YEAR |  | 2021 | [46 empty] | YEAR |  | 2022
WORK PHASE |  | LINE NUMBERS | JAN | FEB |  | MARCH |  | APRIL |  |  | MAY |  | JUNE | JULY | AUGUST | [14 empty] | SEPTEMBER | [6 empty] | OCTOBER | [12 empty] | NOV | DEC | JAN | FEB |  | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOV | DEC
NO. | DESCRIPTION
1 | Miscellaneous | 10-20, 60-130, 160, 210-230 | [6 empty] | 0 | [38 empty] | 112
92
2 | Excavation and Drainage
[17 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 | Base and Pavement
4 | Pedestrian Facilities | 30, 170-200 | [7 empty] | 5 | [5 empty] | 61
5 | Traffic Safety | 40, 50 | [9 empty] | 19 | [18 empty] | 81
6 | Pavement Markings | 140-150, 240-390 | [18 empty] | 81 | [13 empty] | 92
7 | Bridges/Retaining Walls
Add Option #1
5 | Traffic Safety | 40, 50 | [19 empty] | 81 | [15 empty] | 101
[36 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | Pavement Markings | 140-150, 240-390 | [30 empty] | 101 | [13 empty] | 112
| LET: | 2021-02-01
| Anticipated NOA: | 2021-03-01
| Anticipated NTP/BCT: | 2021-05-01
| Working Days: | 92 (Base)
172
MONTH |  |  | JAN | FEB |  | MARCH |  | APRIL |  |  | MAY |  | JUNE | JULY | AUGUST | [14 empty] | SEPTEMBER | [6 empty] | OCTOBER | [12 empty] | NOV | DEC | JAN | FEB |  | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOV | DEC | WORKING
ANTICIPATED WORKING DAYS PER MONTH |  |  | 6 | 7 |  | 11 |  | 15 |  |  | 19 |  | 20 | 21 | 21 | [14 empty] | 20 | [6 empty] | 16 | [12 empty] | 11 | 5 | 6 | 7 |  | 11 | 15 | 19 | 20 | 21 | 21 | 20 | 16 | 11 | 5 | DAYS
PER YEAR
NOTE: THE ANTICIPATED WORKING DAYS SHOWN ON THIS SCHEDULE ARE INFORMATIONAL PURPOSES ONLY.
THE ACTUAL WORKING DAY TOTAL AS ASSESSED BY THE PROJECT ENGINEER ON FORM CSD-765 SHALL GOVERN.
EVERYTHING ABOVE THIS ROW IS REQUIRED TO BE SUBMITTED AND APPROVED AS PART OF THE PRELIMINARY ENGINEERING CONTRACT.
EVERYTHING BELOW THIS ROW SHOULD BE ADDED TO THE APPROVED PROGRESS SCHEDULE AS PART OF THE CE&I CONTRACT.
[11 empty] | Startup | [20 empty] | Closeout
1 Principle (part time)
1 Project Engineer (part time)
1 Clerical (part time)
1 Inspector IV