## Table 1
MISSISSIPPI DOT PRODUCTION PARAMETERS
CATEGORY | UNITS | RURAL | URBAN
Mobilization | WD | 3-5 | 3-5
Clearing and Grubbing | WD | 5-15 | 5-10
Small Structures | WD | 5-10 | 5-10
Unclassified & Borrow Excavation
Truck | CY/WD | 3000-5000 | 1500-3000
Scraper | CY/WD | 10,000-12,000
Chemical Treatments -All Types | SY/WD | 10,000-12,000 plus a min. 7-day cure period | 6000-8000 plus a min. 7-day cure period
In-Grade Preparation | SY/WD | 10000
Granular Material
Reconstruction/Bridge Replacement | CY/WD | 1000-2000 | 500-1000
| T/WD | 1500-3000 | 750-1500
All Other Project Types | CY/WD | 3000-4000 | 1500-3000
| T/WD | 4000-5600 | 2500-4000
Shoulders | CY/WD | 1000-1500 | 500-1000
| T/WD | 1000-2200 | 600-1100
Pipe Culverts
36" and less | LF/WD | 125-225 | 100-175
42" and greater | LF/WD | 75-175 | 50-125
Asphalt Paving
Reconstruction/Bridge Replacement | T/WD | 400-800 | 300-700
Full Depth | T/WD | 800-1200 | 600-1000
Overlay | T/WD | 800-1000 | 500-800
Trench Widening | MI/WD | 1mi. (each side of roadway)
Crushed Stone Drainage Layer | LF/WD | 2000-2500 | 1500-2000
| SY/WD | 2600-3400 | 2000-2600
Asphalt Drainage Layer | SY/WD | 3500-4000 | 3000-3500
Concrete Paving
Roadway (24' -28') | SY/WD | 7000-10,000 plus cure | 3500-7000 plus cure
Shoulders (4'- 10') | SY/WD | 4000-6000 plus cure | 2000-4000 plus cure
Punchouts | SY/WD | 70-100 plus cure | 40-70 plus cure
Traffic Stripe |  | 10 Cal. Days for Waiting Period, then 3-10 WD/Project
Miscellaneous
Erosion Control | AC/WD | 5-10 | 3-5
DBST | MI/WD | 2-3
SBST | MI/WD | 3-5
Milling (All Depths) | SY/WD | 7500-10,000 | 5000-7500
Diamond Grinding | SY/WD | 3500-4500 | 2500-3500
Concrete Rubblizing | SY/WD | 2000-3000
Curbs (All Types)
Handform | LF/WD | 125-200 | 75-125
Slipform | LF/WD | 700-1000 | 500-700
Driveways | SY/WD | 50-75 | 30-50
Concrete Sidewalk | SY/WD | 200-400 | 100-200
Cast in Place Rail (Slip Form) | LF/WD | 1000-2000 | 500-1000
Cable Rail | LF/WD |  | 1500-3000
Guard Rail | LF/WD | 300-400 | 200-300
Lead Time for Guardrail Project | WD | 10
Bridge End Section for GR Project | WD | 1/Bridge End
Clean-up | WD | 5
Traffic Signals
Shop Drawings & Fabrication | Month | 4-6 Months/Project
Installation | Cal. Day | 15 /Site
Bridge Painting | SF/WD | 2000-2500 | 1500-2000
Signing
Shop Drawings & Fabrication | Month | 1-3 Months/Project | 1-3 Months/Project
Installation | SF/WD | 600-900 | 300-600
Crack Sealing | LF/WD | 1500-2000 | 1000-1500
Detour Bridge | WD | 2 WD/Span + 3 WD/ Bulkhead
Remove Bridge
Timber Bridge | WD | 1WD/Span
Concrete Bridge | WD | 3WD/Span
Box Culverts
Full Length | CY/WD | 20-30 plus Cure
Extensions | WD/Site | 10-12 plus Cure
Box Bridge
Full Length | CY/WD | 20-40 plus Cure
Extensions | WD/Site | 10-12 plus Cure
Paved Ditch | SY/WD | 140-180
Removal of Concrete Pavement
Punchouts | SY/WD | 225-300 | 150-225
Concrete Removal | SY/WD | 800-1000 | 500-750
Raised Pavement Markers | EA | 900-1000 | 700-900
Removal of Asphalt Pavement | SY/WD | 3000-5000 | 2000-3000
Edge Drains | LF/WD | 3000-4000 | 2000-3000
Ground-in Rumble Strips | MI/WD | 4-6/Side
Fencing
Barbed Wire | LF/WD | 1000
Woven Wire | LF/WD | 750
Chain Link | LF/WD | 700
Bridges
Excavation | CY/WD | 100-300
Test Pile (Project) | WD | 15 WD/Project
Drive Piling
Steel | LF/WD | 250-500
Concrete | LF/WD | 200-400
Footing Piles | EA/WD | 5 to 10
Construct Pile Caps | WD | 2 WD/Intermediate Bent & 3 WD/End Bent
Set Concrete Beams | WD | 1Span/WD
Construct Slab | LF/WD | 10to 20
Construct Rail | LF/WD | 100-200
Structural Steel Beams
Shop Drawings & Fabrication | Months | 6-9 Months
Erection | Months | 1-3 Months
Slope Paving | CY/WD | 30-80
Test Shaft |  | 1month per project
Drilled Shafts
3-ft Diameter & under | LF/WD | 100-150
Over 3-ft Diameter | LF/WD | 50-100
Cure Time must be taken into consideration for the appropriate bridge items