## Read_Me
Template Notes:
In this example a 24-month contract period is anticipated for completion of this hypothetical study. The study used to develop this example may not be the same as examples included elsewhere in the Research Consultant Manual.
WHEN USING THIS FORM FOR THE PROPOSAL:
- Enter proposal specific information in Rows 2-5.
- The Research Task and Subtask columns include the tasks and subtasks developed in the research plan by the Consultant. Columns to the right of Column E represent proposed duration of project. Highlighted cells represent planned months of work to complete the task. Planned work for Consultant and MDOT are shown.
- Insert rows and columns as needed for the proposed project tasks and duration.
- The Work % column represents, for each task or subtask, the amount of work required to complete the given task/subtask relative to the total amount of work required to complete the study, based on labor (not cost). See tab titled Planned Progress Example for guidance on calculating percent complete by task and by month.
As an example, consider Task C1. The Consultant indicates that this subtask will require 25% of the total effort to complete the study. Further, this task will be completed during months 1 through 16 of the project. The consultant indicates that 5%, 15%, 20%, 20% 20% and 20% of the project will be completed in months 1, 3, 4, 5, 11 and 16 of the project respectively. These sum to 100% for this task.
- Planned Progress by Month (row 29) is the cumulative sum of Work % for each task multiplied by the expected monthly completion.
As an example, in Month 1, expected work is:
Task C1: 5% x 25%
+
Task C2a: 10% x 30%
+
Task C6: 15% x 2.5%
Total for Month 1 = 4.6%
Planned Progress Cumulative (Row 30) end of Month 1 = 4.6%
Likewise in Month 2
Task C2a: 10% x 30%
+
Task C6: 10% x 2.5%
Total for Month 2 = 3.3%
Planned Progress Cumulative (Row 30) end of Month 2 = 4.6% + 3.3% = 7.9%
This is repeated likewise through the end of the contract, which will total 100%.
Enter Planned Budget by month (Row 34 in template before changes). If project requires purchase of equipment included in a task/subtask, the planned expenditure for the cost of that equipment should be included in the month during which the Consultant planned to pay for the purchase of that equipment
- All calculations within the spreadsheet must be verified by the Consultant.
WHEN USING THIS FORM FOR QUARTERLY REPORTS:
- Replace "Month from NTP" in Row 8 into actual FY periods.
- Replace the numbered months in row 9 with actual months.
- As the project progresses, enter Percent Completion by Task/Subtask in the rows identified as Actual in Column E. Percent Completion is by hours (and not cost). When a task is completed, Column AE should total to 100%. The Actual Progress and Actual Cumulative Progress will automatically calculate in Rows 31 and 32.
- Enter project budget expended by month in Row titled Actual Budget.

## Proposal Schedule Template
Research Study Title:
State Study Number: |  |  | NTP Date: | [6 empty] | Federal FY: | [7 empty] | QPR Period: |  | N/A for proposal |  |  |  | Overall % Complete: |  |  | 0%
Research Agency:
Principal Investigator:
Task | Task Description | Work % | Status | Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) | [23 empty] | % By Task
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | Estimated | Completed
C1 | Task C1 description | 25% | Planned | Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 1: 5%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 3: 15%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 4: 20%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 5: 20%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 11: 20%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 16: 20% | 100%
|  |  | Actual | [25 empty] | 0%
M1 | Task M1 description | bar: Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 6 to Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 9
C2-A | Subtask 2-A description | 30% | Planned | Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 1: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 2: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 3: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 4: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 5: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 6: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 7: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 12: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 16: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 17: 10% | 100% |  | Study Hours Based on Task and Subtask |  |  | Study Cost Based on Task and Subtask
|  |  | Actual | [25 empty] | 0% | Task | Hours | Percent Work | Task | Cost | Percent Cost
C2-B | Subtask 2-B description | 7.5% | Planned | Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 3: 50%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 4: 50% | 100% |  | Task C1 | 500 | 25% | Task C1 | 60480 | 28.93%
|  |  | Actual | [25 empty] | 0% | Task C2-A | 600 | 30% | Task C2-A | 62208 | 29.75%
C3 | Task 3 description | 12.5% | Planned | Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 5: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 6: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 7: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 8: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 9: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 10: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 11: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 12: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 13: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 14: 10% | 100% |  | Task C2-B | 150 | 7.5% | Task C2-B | 12960 | 6.198%
|  |  | Actual | [25 empty] | 0% | Task C3 | 250 | 12.5% | Task C3 | 21600 | 10.33%
C4 | Task 4 description | 10% | Planned | Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 5: 25%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 6: 25%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 7: 25%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 8: 25% | 100% |  | Task C4 | 200 | 10% | Task C4 | 20736 | 9.917%
|  |  | Actual | [25 empty] | 0% | Task C5 | 200 | 10% | Task C5 | 20736 | 9.917%
C5 | Task 5 description | 10% | Planned | Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 11: 25%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 12: 25%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 13: 25%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 14: 25% | 100% |  | Task C6 | 50 | 2.5% | Task C6 | 5184 | 2.479%
|  |  | Actual | [25 empty] | 0% | Task C7 | 50 | 2.5% | Task C7 | 5184 | 2.479%
C6 | Project Management | 2.5% | Planned | Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 1: 15%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 2: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 3: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 6: 5%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 9: 5%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 10: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 12: 5%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 15: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 18: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 21: 10%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 24: 10% | 100% |  | Total | 2000 | 100% | Total | 209088 | 100%
|  |  | Actual | [25 empty] | 0%
C7 | Final Deliverables | 2.5% | Planned | Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 11: 25%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 19: 25%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 20: 15%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 23: 15%; Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 24: 20% | 100%
Actual
M7 | Review of Draft Deliverables | bar: Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 21 to Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 22
TOTAL |  | 100%
Planned Progress by Month |  |  |  | 4.625% | 3.25% | 10.75% | 11.75% | 11.75% | 6.875% | 6.75% | 3.75% | 1.375% | 1.5% | 9.375% | 6.875% | 3.75% | 3.75% | 0.25% | 8% | 3% | 0.25% | 0.625% | 0.375% | 0.25% | 0% | 0.375% | 0.75%
Planned Progress Cumulative |  |  |  | 4.625% | 7.875% | 18.63% | 30.38% | 42.12% | 49% | 55.75% | 59.5% | 60.88% | 62.38% | 71.75% | 78.62% | 82.38% | 86.12% | 86.37% | 94.37% | 97.37% | 97.62% | 98.25% | 98.62% | 98.87% | 98.87% | 99.25% | 100%
Actual Progress by Month | bar: Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 1 to Schedule by Task Showing Months from Notice to Proceed Date (Schedule shown is combined for Contractor and MDOT Activities) 24
Actual Progress Cumulative
Planned Budget |  |  |  | 9670.32 | 16465.68 | 38942.64 | 63510.48 | 88078.32 | 102453.12 | 116566.56 | 124407.36 | 127282.32 | 130418.64 | 150020.64 | 164395.44 | 172236.24 | 180077.04 | 180599.76 | 197326.8 | 203599.44 | 204122.16 | 205428.96 | 206213.04 | 206735.76 | 206735.76 | 207519.84 | 209088
Actual Budget
Actual
Planned
Template Notes:
In this example a 24-month contract period is anticipated for completion of this hypothetical study. The study used to develop this example may not be the same as examples included elsewhere in the Consultant Manual.
WHEN USING THIS FORM FOR THE PROPOSAL:
- Enter proposal specific information in Rows 2-5.
- The Research Task and Subtask columns include the tasks and subtasks developed in the research plan by the Consultant. Columns to the right of Column E represent proposed duration of project. Highlighted cells represent planned months of work to complete the task. Planned work for Consultant and MDOT are shown.
- Insert rows and columns as needed for the proposed project tasks and duration.
- The Work % column represents, for each task or subtask, the amount of work required to complete the given task/subtask relative to the total amount of work required to complete the study, based on labor (not cost). See the tab titled Planned Progress Example for guidance on calculating percent complete by task and by month.
As an example, consider Task C1. The Consultant indicates that this subtask will require 25% of the total effort to complete the study. Further, this task will be completed during months 1 through 16 of the project. The consultant indicates that 5%, 15%, 20%, 20% 20% and 20% of the project will be completed in months 1, 3, 4, 5, 11 and 16 of the project respectively. These sum to 100% for this task.
- Planned Overall Progress (row 29) is the cumulative sum of Work % for each task multiplied by the expected monthly completion.
As an example, in Month 1, expected work is:
Task C1: 5% x 25%
+
Task C2a: 10% x 30%
+
Task C6: 15% x 2.5%
Total for Month 1 = 4.6%
Cumulative end of Month 1 = 4.6%
Likewise in Month 2
Task C2a: 10% x 30%
+
Task C6: 10% x 2.5%
Total for Month 2 = 3.3%
Cumulative end of Month 2 = 4.6% + 3.3% = 7.9%
This is repeated likewise through the end of the contract, which will total 100%.
Enter Planned Budget by month (Row 34 in template before changes). If project requires purchase of equipment included in a task/subtask, the planned expenditure for the cost of that equipment should be included in the month during which the Consultant planned to pay for the purchase of that equipment
- All calculations within the spreadsheet must be verified by the Consultant.
WHEN USING THIS FORM FOR QUARTERLY REPORTS:
- Replace "Month from NTP" in Row 8 into actual FY periods.
- Replace the numbered months in row 9 with actual months.
- As the project progresses, enter Percent Completion by Task/Subtask in the rows identified as Actual in Column E. Percent Completion is by hours (and not cost). When a task is completed, Column AE should total to 100%. The Actual Progress and Actual Cumulative Progress will automatically calculate in Rows 31 and 32.
- Enter project budget expended by month in Row titled Acutal Budget.

## Planned Progress Example
PLANNED TASK | Planned | Planned Hours by Month
| Total | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
C1 | 500 | 25 | 0 | 75 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C2-A | 600 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C2-B | 150 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C3 | 250 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C4 | 200 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C5 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C6 | 50 | 7.5 | 5 | 5 | 0 | 0 | 2.5 | 0 | 0 | 2.5 | 5 | 0 | 2.5 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0 | 5
C7 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 7.5 | 0 | 0 | 7.5 | 10
Total | 2000 | 92.5 | 65 | 215 | 235 | 235 | 137.5 | 135 | 75 | 27.5 | 30 | 187.5 | 137.5 | 75 | 75 | 5 | 160 | 60 | 5 | 12.5 | 7.5 | 5 | 0 | 7.5 | 15
PLANNED TASK |  | Planned Progress by Month
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
C1 | 1 | 5% | 0% | 15% | 20% | 20% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C2-A | 1 | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C2-B | 1 | 0% | 0% | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C3 | 1 | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C4 | 1 | 0% | 0% | 0% | 0% | 25% | 25% | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C5 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 25% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
C6 | 1 | 15% | 10% | 10% | 0% | 0% | 5% | 0% | 0% | 5% | 10% | 0% | 5% | 0% | 0% | 10% | 0% | 0% | 10% | 0% | 0% | 10% | 0% | 0% | 10%
C7 | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 15% | 0% | 0% | 15% | 20%
Template Notes:
- This template shows an example of calulating planned progress by month and by task subtask.
- Enter budgeted hours by month used in the proposal.
- For each task in the Planned Hours by Month, percent progress is calculated by month.
WHEN USING THIS FORM FOR QUARTERLY REPORTS:
- Replace month number (0, 1, 2, etc.) with actual months (May 22, June 22, etc.).
- Enter hours by month in the "Actual" table. Example shows hours entered for 11 months.
- Copy the formula for actual Cumulative Progress (hours) and cumulative progress (%).