## QPR_Template_schedule_Progress
Research Study Title:
State Study Number: |  |  | NTP Date: | [6 empty] | Federal FY: | [7 empty] | QPR Period: | [5 empty] | Overall % Complete:
Research Agency:
Principal Investigator:
Task | Task Description | Work % | Status | FFY 2022 |  |  |  |  | FFY 2023 | [11 empty] | FFY 2024 | [6 empty] | % By Task
|  |  |  | 2022-05-28 | 2022-06-28 | 2022-07-28 | 2022-08-28 | 2022-09-28 | 2022-10-28 | 2022-11-28 | 2022-12-28 | 2023-01-28 | 2023-02-28 | 2023-03-28 | 2023-04-28 | 2023-05-28 | 2023-06-28 | 2023-07-28 | 2023-08-28 | 2023-09-28 | 2023-10-28 | 2023-11-28 | 2023-12-28 | 2024-01-28 | 2024-02-28 | 2024-03-28 | 2024-04-28 | Estimated | Completed
C1 | Task C1 description | 25% | Planned | 2022-05-28: 5%; 2022-07-28: 15%; 2022-08-28: 20%; 2022-09-28: 20%; 2023-03-28: 20%; 2023-08-28: 20% | 100%
|  |  | Actual | 2022-08-28: 20%; 2023-01-28: 20%; 2023-02-28: 20% |  | 60%
M1 | Task M1 description | bar: 2022-10-28 to 2023-01-28
C2-A | Task 2 description | 30% | Planned | 2022-05-28: 10%; 2022-06-28: 10%; 2022-07-28: 10%; 2022-08-28: 10%; 2022-09-28: 10%; 2022-10-28: 10%; 2022-11-28: 10%; 2023-04-28: 10%; 2023-08-28: 10%; 2023-09-28: 10% | 100% |  | Study Hours Based on Task and Subtask |  |  | Study Cost Based on Task and Subtask
|  |  | Actual | 2022-08-28: 20%; 2022-09-28: 20%; 2023-01-28: 20%; 2023-02-28: 20% |  | 80% | Task | Hours | Percent Work | Task | Cost | Percent Cost
C2-B | Task 3 description | 7.5% | Planned | 2022-07-28: 50%; 2022-08-28: 50% | 100% |  | Task C1 | 500 | 25% | Task C1 | 60480 | 28.93%
|  |  | Actual | 2022-07-28: 50%; 2022-08-28: 50% |  | 100% | Task C2-A | 600 | 30% | Task C2-A | 62208 | 29.75%
C3 | Task 3 description | 12.5% | Planned | 2022-09-28: 10%; 2022-10-28: 10%; 2022-11-28: 10%; 2022-12-28: 10%; 2023-01-28: 10%; 2023-02-28: 10%; 2023-03-28: 10%; 2023-04-28: 10%; 2023-05-28: 10%; 2023-06-28: 10% | 100% |  | Task C2-B | 150 | 7.5% | Task C2-B | 12960 | 6.198%
|  |  | Actual | 2022-12-28: 10%; 2023-01-28: 10%; 2023-02-28: 10% |  | 30% | Task C3 | 250 | 12.5% | Task C3 | 21600 | 10.33%
C4 | Task 4 description | 10% | Planned | 2022-09-28: 25%; 2022-10-28: 25%; 2022-11-28: 25%; 2022-12-28: 25% | 100% |  | Task C4 | 200 | 10% | Task C4 | 20736 | 9.917%
|  |  | Actual | 2022-09-28: 25%; 2022-10-28: 50%; 2022-11-28: 25% |  | 100% | Task C5 | 200 | 10% | Task C5 | 20736 | 9.917%
C5 | Task 5 description | 10% | Planned | 2023-03-28: 25%; 2023-04-28: 25%; 2023-05-28: 25%; 2023-06-28: 25% | 100% |  | Task C6 | 50 | 2.5% | Task C6 | 5184 | 2.479%
|  |  | Actual | 2022-08-28: 10%; 2022-09-28: 10%; 2023-02-28: 25% |  | 45% | Task C7 | 50 | 2.5% | Task C7 | 5184 | 2.479%
C6 | Project Management | 2.5% | Planned | 2022-05-28: 15%; 2022-06-28: 10%; 2022-07-28: 10%; 2022-10-28: 5%; 2023-01-28: 5%; 2023-02-28: 10%; 2023-04-28: 5%; 2023-07-28: 10%; 2023-10-28: 10%; 2024-01-28: 10%; 2024-04-28: 10% | 100% |  | Total | 2000 | 100% | Total | 209088 | 100%
|  |  | Actual | 2022-05-28: 10%; 2022-06-28: 5%; 2022-07-28: 5%; 2022-10-28: 5%; 2023-01-28: 5%; 2023-03-28: 5% |  | 35%
C7 | Final Deliverables | 2.5% | Planned | 2023-03-28: 25%; 2023-11-28: 25%; 2023-12-28: 15%; 2024-03-28: 15%; 2024-04-28: 20% | 100%
|  |  | Actual | 2022-09-28: 5%; 2023-02-28: 15%
M7 | Review of Draft Deliverables | bar: 2024-01-28 to 2024-02-28
TOTAL |  | 100%
Planned Progress by Month |  |  |  | 4.625% | 3.25% | 10.75% | 11.75% | 11.75% | 6.875% | 6.75% | 3.75% | 1.375% | 1.5% | 9.375% | 6.875% | 3.75% | 3.75% | 0.25% | 8% | 3% | 0.25% | 0.625% | 0.375% | 0.25% | 0% | 0.375% | 0.75%
Planned Progress Cumulative |  |  |  | 4.625% | 7.875% | 18.63% | 30.38% | 42.12% | 49% | 55.75% | 59.5% | 60.88% | 62.38% | 71.75% | 78.62% | 82.38% | 86.12% | 86.37% | 94.37% | 97.37% | 97.62% | 98.25% | 98.62% | 98.87% | 98.87% | 99.25% | 100%
Actual Progress by Month |  |  |  | 0.25% | 0.125% | 3.875% | 15.75% | 9.625% | 5.125% | 2.5% | 1.25% | 12.38% | 15.12% | 0.125% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Actual Progress Cumulative |  |  |  | 2022-05-28: 0.25%; 2022-06-28: 0.375%; 2022-07-28: 4.25%; 2022-08-28: 20%; 2022-09-28: 29.62%; 2022-10-28: 34.75%; 2022-11-28: 37.25%; 2022-12-28: 38.5%; 2023-01-28: 50.88%; 2023-02-28: 66%; 2023-03-28: 66.12%
Planned Budget |  |  |  | 9670.32 | 16465.68 | 38942.64 | 63510.48 | 88078.32 | 102453.12 | 116566.56 | 124407.36 | 127282.32 | 130418.64 | 150020.64 | 164395.44 | 172236.24 | 180077.04 | 180599.76 | 197326.8 | 203599.44 | 204122.16 | 205428.96 | 206213.04 | 206735.76 | 206735.76 | 207519.84 | 209088
Actual Budget |  |  |  | 2022-05-28: 522.72; 2022-06-28: 784.08; 2022-07-28: 10218; 2022-08-28: 41817.6; 2022-09-28: 61942.32; 2022-10-28: 72658.08; 2022-11-28: 77885.28; 2022-12-28: 80498.88; 2023-01-28: 106373.52; 2023-02-28: 137998.08; 2023-03-28: 138259.44
Actual
Planned
Template Notes:
Follow the guidance based on sample data and revise as appropriate. This template is a sample of how the Gantt Chart created for the proposal should be updated to generate actual vs planned schedule, chart for actual vs planned progress, and chart for actual vs planned budget expended for Quarterly Progress Reports, Annual Reports, and supporting documentation with each submission of an invoice.
WHEN USING THIS FORM FOR QUARTERLY/ANNUAL REPORTS:
- Replace "Month from NTP" in Row 8 into actual FY periods
- Replace the numbered months in row 9 with actual months
- As the project progresses, enter Percent Completion by Task/Subtask in the row identified as Actual in Column E. Percent completed is by labor hours (and not by cost). When a task is completed, Column AE should total to 100%. Example for calculation of Actual Progress is on sheet titled Actual Progress Example.
- The Actual Progress and Actual Cumulative Progress will automatically calculate in Rows 31 and 32
- Enter Actual Budget expended by month.
- All calculations within the spreadsheet must be verified by the Consultant when rows and columns are inserted/deleted from the template.

## Actual Progress Example
Actual Task | Actual | Actual Hours by Month
| Total | 2022-05-28 | 2022-06-28 | 2022-07-28 | 2022-08-28 | 2022-09-28 | 2022-10-28 | 2022-11-28 | 2022-12-28 | 2023-01-28 | 2023-02-28 | 2023-03-28 | 2023-04-28 | 2023-05-28 | 2023-06-28 | 2023-07-28 | 2023-08-28 | 2023-09-28 | 2023-10-28 | 2023-11-28 | 2023-12-28 | 2024-01-28 | 2024-02-28 | 2024-03-28 | 2024-04-28
C1 | 500 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100 | 100 | 0
C2-A | 600 | 0 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 120 | 120 | 0
C2-B | 150 | 0 | 0 | 75 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C3 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 0
C4 | 200 | 0 | 0 | 0 | 0 | 50 | 100 | 50 | 0 | 0 | 0 | 0
C5 | 200 | 0 | 0 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 50 | 0
C6 | 50 | 5 | 2.5 | 2.5 | 0 | 0 | 2.5 | 0 | 0 | 2.5 | 0 | 2.5
C7 | 50 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 7.5 | 0
Total | 2000 | 5 | 2.5 | 77.5 | 315 | 192.5 | 102.5 | 50 | 25 | 247.5 | 302.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual Task |  | Actual Progress by Month
|  | 2022-05-28 | 2022-06-28 | 2022-07-28 | 2022-08-28 | 2022-09-28 | 2022-10-28 | 2022-11-28 | 2022-12-28 | 2023-01-28 | 2023-02-28 | 2023-03-28 | 2023-04-28 | 2023-05-28 | 2023-06-28 | 2023-07-28 | 2023-08-28 | 2023-09-28 | 2023-10-28 | 2023-11-28 | 2023-12-28 | 2024-01-28 | 2024-02-28 | 2024-03-28 | 2024-04-28
C1 | 0.6 | 2022-05-28: 0%; 2022-06-28: 0%; 2022-07-28: 0%; 2022-08-28: 20%; 2022-09-28: 0%; 2022-10-28: 0%; 2022-11-28: 0%; 2022-12-28: 0%; 2023-01-28: 20%; 2023-02-28: 20%; 2023-03-28: 0%
C2-A | 0.8 | 2022-05-28: 0%; 2022-06-28: 0%; 2022-07-28: 0%; 2022-08-28: 20%; 2022-09-28: 20%; 2022-10-28: 0%; 2022-11-28: 0%; 2022-12-28: 0%; 2023-01-28: 20%; 2023-02-28: 20%; 2023-03-28: 0%
C2-B | 1 | 2022-05-28: 0%; 2022-06-28: 0%; 2022-07-28: 50%; 2022-08-28: 50%; 2022-09-28: 0%; 2022-10-28: 0%; 2022-11-28: 0%; 2022-12-28: 0%; 2023-01-28: 0%; 2023-02-28: 0%; 2023-03-28: 0%
C3 | 0.3 | 2022-05-28: 0%; 2022-06-28: 0%; 2022-07-28: 0%; 2022-08-28: 0%; 2022-09-28: 0%; 2022-10-28: 0%; 2022-11-28: 0%; 2022-12-28: 10%; 2023-01-28: 10%; 2023-02-28: 10%; 2023-03-28: 0%
C4 | 1 | 2022-05-28: 0%; 2022-06-28: 0%; 2022-07-28: 0%; 2022-08-28: 0%; 2022-09-28: 25%; 2022-10-28: 50%; 2022-11-28: 25%; 2022-12-28: 0%; 2023-01-28: 0%; 2023-02-28: 0%; 2023-03-28: 0%
C5 | 0.45 | 2022-05-28: 0%; 2022-06-28: 0%; 2022-07-28: 0%; 2022-08-28: 10%; 2022-09-28: 10%; 2022-10-28: 0%; 2022-11-28: 0%; 2022-12-28: 0%; 2023-01-28: 0%; 2023-02-28: 25%; 2023-03-28: 0%
C6 | 0.35 | 2022-05-28: 10%; 2022-06-28: 5%; 2022-07-28: 5%; 2022-08-28: 0%; 2022-09-28: 0%; 2022-10-28: 5%; 2022-11-28: 0%; 2022-12-28: 0%; 2023-01-28: 5%; 2023-02-28: 0%; 2023-03-28: 5%
C7 | 0.2 | 2022-05-28: 0%; 2022-06-28: 0%; 2022-07-28: 0%; 2022-08-28: 0%; 2022-09-28: 5%; 2022-10-28: 0%; 2022-11-28: 0%; 2022-12-28: 0%; 2023-01-28: 0%; 2023-02-28: 15%; 2023-03-28: 0%
Template Notes:
WHEN USING THIS FORM FOR QUARTERLY/ANNUAL REPORTS:
- Enter hours by month in the "Actual" table. Example shows hours entered for 11 months.
- Copy the formula for Actual Progress (%)